DYNAMO

DMSi Customer Support Transformation

Implementation Plan & Execution Roadmap

Phase: Execution
March 2026

# 1. Executive Summary

This Implementation Plan translates the Operating Model Redesign recommendations into an actionable, phased execution roadmap spanning 12 months. The transformation is organized into five phases, each building systematically toward the target state while managing risk.

Target Outcomes:

- Recurring annual savings of $794k–$970k through 25–30% handling effort reduction

- MTTR P50/P75 for Enterprise cases reduced from days to hours

- Migration to modern SaaS support platform with integrated AI capabilities

- Formalized customer segmentation with differentiated SLOs by tier

Investment Summary:

| Category | One-Time | Annual |
| --- | --- | --- |
| SaaS Platform Implementation | $200,000 | $70,000 |
| Agentic AI Layer Integration | $100,000 | $20,000 |
| Change Management & Training | $50,000 | — |
| Total | $350,000 | $90,000 |

# 2. Program Governance Structure

Successful execution requires clear governance with defined roles, decision rights, and regular cadences.

2.1 Key Roles

| Role | Responsibility | Assignment | Name |
| --- | --- | --- | --- |
| Executive Sponsor | Budget authority, escalation resolution | VP Customer Experience | Jared Plucknett |
| Transformation Lead (Workstream lead) | End to End implementation program management | Dynamo | Adam Saad/ Dynamo Team |
| Support Change Lead | Program management, Agent communication, training | Senior Support Supervisor | Amanda Briggs |
| Engineering Lead | Incident process, tooling integration | Engineering Manager | Bryan and Andy |
| Internal Product Lead | Roadmap alignment, triad participation | Product Manager | “Jason Niemi”?? |

2.2 Meeting Cadences

| Meeting | Frequency | Attendees | Purpose |
| --- | --- | --- | --- |
| Workstream Standups | 2x/week | Workstream members when applicable | Task coordination |
| Control Room | Every Sprint (Bi weekly) | All leads + Sponsor | Status, blockers, decisions |
| Steering Committee | Monthly | Sponsor + Exec team | Strategic decisions |
| Agility Triad | Monthly | Support/Eng/Product | Cross-functional issues |

# 3. Implementation Phases Overview

| Phase | Timeline | Focus | Key Deliverables |
| --- | --- | --- | --- |
| Phase 0: Alignment | Weeks 1-4 | Foundation, instrumentation | Scorecard v0, Segmentation tags, Team formed |
| Phase 1: Prove Flow | Months 1 - 2 | MIM function, initial pods, SLOs | MIM live, Agility Core pod, Enterprise SLOs |
| Phase 2: Scale | Months 3+ | Full pods, segmentations | All pods, segmentations operational |
| Phase 3: Tooling | Months 2-5 | AI layer, SaaS selection | Vendors selected |
| Phase 4: Deploy & Migrate | Months 5-12 | Platform implementation, 360 retirement | AI deployed, New platform live, 25-30% efficiency |

# 4. Phase 0: Alignment & Instrumentation (Weeks 1-4)

Objective: Establish foundation through leadership alignment, instrumentation, and team formation.

4.1 Workstream: Leadership Alignment

| # | Activity | Owner | Sprint | Deliverable |
| --- | --- | --- | --- | --- |
| 0.1 | Kick-off meeting; agree governance cadences, Identify Engineering and Product counterparts | Trans Lead, Sponsor | S1 | Governance charter |

4.2 Workstream: Instrumentation & Baseline

| # | Activity | Owner | Sprint | Deliverable |
| --- | --- | --- | --- | --- |
| 0.2 | Publish current baseline Scorecard v0 to leadership | Trans Lead | S1 | Baseline scorecard |

4.3 Workstream: Customer Segmentation Setup

| # | Activity | Owner | Sprint | Deliverable |
| --- | --- | --- | --- | --- |
| 0.3.1 | Finalize Enterprise vs Commercial criteria | Trans Lead | S1 | Segmentation rules |
| 0.3.2 | Create segment attribute in 360 | Support Lead | S2 | Field configured |
| 0.3.3 | Tag all customer accounts with segment | Support Lead | S2 | All accounts tagged |
| 0.3.4 | Validate with Account Management (top 50) | Trans Lead, Support Lead | S2 | Validation sign-off |

Phase 0 Exit Criteria:

- Transformation Lead assigned and operating

- Governance charter signed by all leads

- Support Scorecard v0 published with baseline metrics

- All customer accounts tagged with segment

- Current incident process documented

# 5. Phase 1: Prove Flow & Communications (Months 1-3)

Objective: Demonstrate early wins through improved incident communications, initial pods, and SLO adoption.

5.1 Workstream: Major Incident Management

| # | Activity | Owner | Month | Deliverable |
| --- | --- | --- | --- | --- |
| 1.1.1 | Define MIM role and escalation criteria | Trans Lead, Support Lead | M1 | MIM role description |
| 1.1.2 | Create incident communication templates and communication plan | Trans Lead, Support Lead | M1 | Template library, comms plan |
| 1.1.3 | Configure paging for Sev-1/2 to MIM rotation | Eng Lead | M1 | Paging configured |
| 1.1.4 | Train 2-3 agents on MIM responsibilities | Support Lead | M1-2 | Trained MIM pool |
| 1.1.5 | Launch MIM function (15-30 min first update) | Support Lead | M2 | MIM function live |
| 1.1.6 | Define RCA SLO (draft 48-72h, final 5 BD) | Trans Lead, Eng Lead | M2 | RCA process doc |
| 1.1.7 | Track RCA coverage %; target 80%+ Sev-1/2 | Trans Lead, Support Lead, Eng Lead | M2-3 | RCA in Scorecard |

5.2 Workstream: Initial Pod Structure

| # | Activity | Owner | Month | Deliverable |
| --- | --- | --- | --- | --- |
| 1.2.1 | Design Agility Core pod (agents, scope) | Trans Lead | M1 | Pod design doc |
| 1.2.2 | Design Other Products desk | Trans Lead | M1 | Desk design doc |
| 1.2.3 | Create product/module routing tags in 360 | Support Lead | M1-2 | Tags configured |
| 1.2.4 | Assign agents to Agility Core (8-10) | Support Lead | M2 | Pod roster |
| 1.2.5 | Implement routing for Agility Core cases | Support Lead | M2 | Routing live |
| 1.2.6 | Stand up Other Products desk (4-6) | Support Lead | M2-3 | Desk operational |

5.3 Workstream: SLO Adoption

| # | Activity | Owner | Month | Deliverable |
| --- | --- | --- | --- | --- |
| 1.3.1 | Publish Enterprise vs Commercial SLOs internally | Trans Lead, Support Lead | M1 | SLO matrix |
| 1.3.2 | Configure SLA clocks in 360 by segment | Support Lead | M2 | SLA tracking enabled |
| 1.3.3 | Train supervisors on SLO expectations | Support Lead | M2 | Training complete |
| 1.3.4 | Measure first response by segment | Support Lead | M2-3 | Segment metrics live |
| 1.3.5 | Weekly SLO review in Control Room | Support Lead | M3+ | Review established |

Phase 1 Exit Criteria:

- MIM operational with P1 first update trending toward ≤60 min

- Agility Core pod and Other Products desk routing cases

- Enterprise vs Commercial SLOs published and measured

- FCR tracking enabled with baseline

- 5-8% handling effort reduction visible

# 6. Phase 2: Scaling (Month 3+)

Objective: Scale operating model across all Agility modules

6.1 Workstream: Full Pod Expansion

| # | Activity | Owner | Month | Deliverable |
| --- | --- | --- | --- | --- |
| 2.1.1 | Design Reporting & Printing pod | Trans Lead | M3-4 | Pod design doc |
| 2.1.2 | Design WMS & Integrations pod | Trans Lead | M3-4 | Pod design doc |
| 2.1.3 | Stand up Reporting & Printing pod | Supervisors | M4-5 | Pod operational |
| 2.1.4 | Stand up WMS & Integrations pod | Supervisors | M5-6 | Pod operational |
| 2.1.5 | Implement Enterprise fast-lane overlay | Trans Lead | M5-6 | Fast-lane active |
| 2.1.6 | Refine severity-based routing | Support Ops | M6 | Routing optimized |

Phase 2 Exit Criteria:

- All Agility pods operational

- 15% handling reduction (~$518k annualized)

# 7. Phase 3: Tooling (Month 3+)

7.1 Workstream: SaaS Platform Selection

| # | Activity | Owner | Month | Deliverable |
| --- | --- | --- | --- | --- |
| 3.1.1 | Complete SaaS Support Suite RFP | Trans Lead | M4-5 | RFP issued |
| 3.1.2 | Vendor demos and scoring | Committee | M5-6 | Scorecard |
| 3.1.3 | Reference checks | Trans Lead | M6 | Reference notes |
| 3.1.4 | TCO analysis and recommendation | Trans Lead | M6-7 | TCO model |
| 3.1.5 | Steering Committee decision | Sponsor | M7 | Vendor selected |
| 3.1.6 | Contract negotiation | Sponsor/Legal | M7-8 | Contract signed |
| 3.1.7 | Design migration blueprint | Trans Lead | M8-9 | Migration plan |

7.2 Workstream: Agentic AI Layer

| # | Activity | Owner | Month | Deliverable |
| --- | --- | --- | --- | --- |
| 3.2.1 | Complete Agentic AI vendor RFP | Trans Lead | M3-4 | Vendor selected |
| 3.2.2 | Contract negotiation and procurement | Sponsor | M4-5 | Contract signed |
| 3.2.3 | Integration design (API to 360, KB) | Eng Lead | M5 | Integration spec |
| 3.2.4 | Pilot with Agility Core pod (10 agents) | Trans Lead | M5-6 | Pilot live |
| 3.2.5 | Measure pilot impact | Trans Lead | M6-7 | Pilot assessment |
| 3.2.6 | Refine prompts and workflows | Trans Lead | M7 | Refined config |
| 3.2.7 | Full rollout to all pods | Trans Lead | M7-8 | AI fully deployed |

Phase 3 Exit Criteria:

- SaaS & AI vendor selected with signed contract

- Migration blueprint approved

# 8. Phase 4: Platform Migration (Months 9-18)

Objective: Implement new SaaS platform, migrate Support off 360, institutionalize changes.

8.1 Workstream: Platform Configuration

| # | Activity | Owner | Month | Deliverable |
| --- | --- | --- | --- | --- |
| 4.1.1 | Configure segments and entitlements | Vendor/Ops | M5-6 | Segments configured |
| 4.1.2 | Configure skills-based routing | Vendor/Ops | M5-6 | Routing configured |
| 4.1.3 | Configure SLA clocks | Vendor/Ops | M5-6 | SLAs configured |
| 4.1.4 | Migrate knowledge base content | Support SMEs | M5-6 | KB populated |
| 4.1.5 | Configure guided flows | Support SMEs | M5-6 | Flows live |
| 4.1.6 | Integrate SSO, customer data | Eng Lead | M6-7 | Integrations tested |
| 4.1.7 | Integrate monitoring/incident tools | Eng Lead | M6-7 | Integrations tested |

8.2 Workstream: Migration Execution

| # | Activity | Owner | Month | Deliverable |
| --- | --- | --- | --- | --- |
| 4.2.1 | Train pilot group | Support Lead | M7-8 | Pilot group trained |
| 4.2.2 | Execute pilot migration | Support Lead | M8 | Pilot live |
| 4.2.3 | Monitor pilot performance | Trans Lead, Support Lead | M9-10 | Pilot assessment |
| 4.2.4 | Address issues, refine config | Trans Lead, Support Lead, Eng Lead | M9-10 | Issues resolved |
| 4.2.5 | Train remaining agents | Support Lead | M9-10 | All agents trained |
| 4.2.6 | Execute full migration | Eng Lead | M10 | Migration complete |
| 4.2.7 | Freeze 360 for new Support tickets | Eng Lead | M12 | 360 frozen |

8.3 Workstream: Institutionalization

| # | Activity | Owner | Month | Deliverable |
| --- | --- | --- | --- | --- |
| 4.3.1 | Update Scorecard for new platform | Trans Lead, Support Lead | M12 | New Scorecard |
| 4.3.2 | Benefits realization assessment | Trans Lead | M12 | Benefits report |
| 4.3.2 | Close transformation program | Sponsor | M12 | Program closed |

# 9. Master Gantt Chart

The following provides a high-level timeline view. Detailed schedules maintained in project tool.

# 10. Risk Register

| ID | Risk | Impact | Likelihood | Mitigation |
| --- | --- | --- | --- | --- |
| R1 | Under-resourcing transformation | High | Medium | Dedicated Trans Lead; backfill Support |
| R2 | Cultural resistance from Eng/Product | High | Medium | Exec sponsorship; quick wins |
| R3 | 360 limitations block progress | Medium | High | Layer capabilities; accelerate SaaS |
| R4 | SaaS migration disrupts service | High | Medium | Pilot first; hypercare period |
| R5 | AI layer underperforms | Medium | Medium | Pilot subset; human review; fallback |
| R6 | Strategic customer dissatisfaction | High | Low | Named TAMs; proactive comms |

# 11. Success Metrics

Financial Metrics:

| Metric | Baseline | Phase 1 Target | Phase 3 Target |
| --- | --- | --- | --- |
| $/case (labor) | $105 | $92 (-12%) | $74 (-30%) |
| Handling reduction | 0% | 15% | 25-30% |
| FTE capacity freed | 0 | 7.2 | 12-14 |

Flow Metrics:

| Metric | Baseline | Phase 1 Target | Phase 3 Target |
| --- | --- | --- | --- |
| MTTR P50 (Enterprise) | ~57 hours | 36 hours | 8 hours |
| P1 First Update Median | ~3.2 hours | ≤60 min | ≤30 min |
| FCR% | TBD | +5 pts | +10 pts |

Reliability Metrics:

| Metric | Baseline | Phase 1 Target | Phase 3 Target |
| --- | --- | --- | --- |
| RCA Coverage (Sev-1/2) | 84.6% | 90% | 95% |
| RCA Coverage (All) | 44.8% | 60% | 80% |