DYNAMO

DMSi Operational Readiness — Workstream A (Engineering Foundations)

Implementation Plan & Execution Roadmap

Phase: Execution

March 2026

# 1. Executive Summary

This implementation plan translates Workstream A capabilities — Work Management, Visibility Infrastructure, Pipeline Automation, and Learning System — into an execution roadmap. Program governance labels this workstream A: Platform Reliability (with the same scope as the engineering foundations described here and in the capability map). Work is tracked as outcomes with explicit dependencies (must / should / contingent), not as a single linear stage sequence.

Workstream A intent (from capability map):

- Work Management: A single trusted view of planned work, capacity, and prioritization so commitments are visible and followed through.

- Visibility Infrastructure: Trusted real-time health, alerting, and (over time) proactive detection before customers report issues.

- Pipeline Automation: Configuration changes flow through tested, approved, auditable automation (NGINX proof-of-concept first; pattern replication is conditional).

- Learning System: Systematic learning from incidents (SLOs, playbooks, error budgets); gated on other Workstream A progress and Workstream B/C alignment per the capability map prerequisites.

Program milestone alignment (from capability map state):

| Milestone | Label |
| --- | --- |
| M2 | Establish the Structure |
| M3 | Build the Foundation |
| M4 | Operationalize Intelligence |
| M5 | Support Excellence |
| M6 | Modernized Release Management |
| M7 | Completion |

# 2. Governance — Workstream A only

Successful delivery requires clear roles and cadences on both sides. The following is extracted and scoped to Workstream A from DMSi Program Governance (Draft v0.4) and aligned with the team's existing practices (daily standups, sprint demos). Program-level ceremonies (Hilltop, DMSi Coordination Sync across all workstreams) are referenced for context only; detail stays in the program governance document.

2.1 Key Role

| Role | Responsibility | Assignment | Name |
| --- | --- | --- | --- |
| Executive Sponsor | Budget authority, escalation resolution |  | Brent Heavican |
| Engagement Lead |  | Dynamo | Cameron Ludwig |
| Transformation Lead (Workstream lead) | End to End implementation program management | Dynamo | Dan Carnes |
| Project Management | Program management, Agent communication, training | Senior Support Supervisor | Nick Kramer |
| Engineering Lead | Incident process, tooling integration | Dynamo | Brent Adkisson |

2.2 Meeting cadences — Workstream A

| Meeting | Frequency | Attendees | Purpose |
| --- | --- | --- | --- |
| Team standup | Daily | Core delivery team (DMSi + Dynamo) | Coordination, blockers, handoffs |
| Dynamo internal sprint demo | Per sprint; first session April 1, 2026 | Dynamo | Internal quality gate before client demos |
| DMSi sprint demo | Per sprint; starting April 3, 2026 | DMSi stakeholders + Dynamo | Increment review, stakeholder visibility |

# 3. Implementation phases overview

| Milestone | Target | What (Workstream A relevant) | Outcome |
| --- | --- | --- | --- |
| M1 | Kickoff | SOW executed, Engagement Kickoff |  |
| M2 | Month 2 | - Engineering Scorecard operational (A, D) - Baseline metrics collected (A, B) - Current state documentation (A, B) - Deployment mapping begun (A) - A2W/Frameworks telemetry strategy begun (A) | Visibility and prioritization system for how engineering capacity is used and where it is consumed by preventable work. Tribal knowledge capture underway. |
| M3 | Month 4 | - Code-as-Config pipeline built (ready to deploy) (A) - Observability documented (A) - Deployment mapping and documentation complete (A) - A2W/Frameworks telemetry strategy complete (A) - TierPoint SLA evaluation complete (A) | Technical foundation for reliable configuration deployment is in place. Observability design for A2W is complete and ready for deployment. |
| M4 | Month 8 | - Code-as-Config operational (>=80% compliance, 4 weeks) (A) - PagerDuty AIOps configured and deployed (A) - Monitoring platform decision complete (CheckMK 2.4 vs. APM) (A) | Configuration-related incidents reduced from baseline. AI-assisted alert correlation and noise reduction. Decision on monitoring platform. |
| M5 | Month 12 | - Monitoring operational (MTTD <=10 min) - CI/CD pipeline built | Proactive communication by support to customers when there is a problem. Engineering reinvestment into planned work. |
| M6 | Month 16 | - CI/CD operational (>=80% compliance, 4 weeks) - Change Failure Rate (CFR) <=15% - Scripted deployments standard | Deployments no longer require heroics or key-person availability. Automated, reliable, and routine with automated rollback. |
| M7 | Month 18 | - Automated remediation for top incident types - DORA metrics tracked, visible, and improving - Knowledge transfer | Engineering at industry standards with continuous improvement learning loop. Operational foundation to support 40% growth without linear headcount increase. |

| Phase | Milestone | Timing | Focus | Key Deliverables |
| --- | --- | --- | --- | --- |
| Phase 0: Alignment and Access | M2 | Weeks 1-4 | Access, inventories, architecture, governance | WM discovery complete; VI foundation planning; PA POC and security baseline; LS prerequisites acknowledged |
| Phase 1: Foundation Built | M3 | Weeks 3-10+ | Instrumentation, inventory, platform decisions | WM tool configured; VI platform deployed and hosts instrumented; PA configs in VCS; milestone progress toward M3 |
| Phase 2: Pipelines and Signals Live | M4 | Overlapping | Build/deploy/drift; logs/synthetics/APM | PA build + deploy + drift operational; VI data quality and baselines; M4-aligned capabilities |
| Phase 3: Enforce, Trust, Scale | M5-M6 | Conditional / iterative | Reliability validation, config-as-code enforcement, decommissioning | Pipeline reliability validated and enforced; VI alerting tuned and proactive ops validated; WM board accuracy + scorecard; M5-M6 alignment |
| Phase 4: Advanced / Replicate | M7 | Trigger-based | Pattern replication, predictive ops, learning loop | Pipeline pattern replication (leadership decision); predictive operations; LS later stages; knowledge transfer |

# 4. Phase 0: Alignment, access, and instrumentation

Objective: Establish access, shared understanding, and baseline artifacts so parallel work (WM, VI, PA) does not build on assumptions.

4.1 Workstream: Work Management

| # | Activity | Owner | Timing | Deliverable |
| --- | --- | --- | --- | --- |
| WM-0.1 | Complete current-state discovery and workflow mapping | Dynamo + Bryan + Andy | Weeks 1–2 | WM-OC-01 complete (per WM-WSB) |
| WM-0.2 | Define operating model, taxonomy, triage design | Dynamo + DMSi | Weeks 2–3 | WM-OC-02 complete |
| WM-0.3 | Resolve tool path (GitHub vs Jira decision per capability map blocker) | Leads + DMSi | Week 3–4 | Decision recorded; WM-OC-03 unblocked |

Phase 0 Exit Criteria:

- Work intake channels mapped and existing tracking mechanisms identified (WM-OC-01)

- Pain points documented; 360 case data evaluated; side-door work patterns identified (WM-OC-01)

- Workflow states, work categories, and triage ceremony designed and agreed (WM-OC-02)

- WIP limits set, capacity allocation model documented, and one-page operating agreement committed (WM-OC-02)

- The tool direction is clear enough to begin WM-OC-03 configuration

4.2 Workstream: Visibility Infrastructure & Proactive Detection

| # | Activity | Owner | Timing | Deliverable |
| --- | --- | --- | --- | --- |
| VI-0.1 | Environment inventory, architecture, integration design | Dynamo + Andy / Robin | Weeks 1–2 | VI-OC-01 deliverables (VI-WSB) |
| VI-0.2 | Telemetry strategy and licensing | Dynamo + Brent | Weeks 2–3 | VI-OC-02 complete |
| VI-0.3 | PagerDuty AIOps track (active band Mar 9 – Apr 20 per WBS) | Dynamo + DMSi | Overlapping | Progress on VI-OC-16 |

Exit Criteria:

- Environment inventory complete, reviewed, and signed off (VI-OC-01)

- Dynatrace architecture design and integration architecture documented (VI-OC-01)

- ABL telemetry evaluation complete; Dynatrace licensing procured (VI-OC-02)

- Log retention and compliance requirements confirmed; RBAC model defined (VI-OC-02)

- Path to VI-OC-03 (Dynatrace platform deployment) agreed

4.3 Workstream: Pipeline Automation

| # | Activity | Owner | Timing | Deliverable |
| --- | --- | --- | --- | --- |
| PA-0.1 | Infrastructure & architecture POC | Dynamo + DMSi | Weeks 1–2 | PA-OC-00 success criteria (Jira WSA-3758) |
| PA-0.2 | Foundation access, security baseline, SOC 2 alignment | Dynamo + Andy | Weeks 3–5 | PA-OC-01 complete |
| PA-0.3 | Configuration inventory + credential mapping | Dynamo + Andy | Weeks 2–4 | PA-OC-02 progress / complete |

Exit Criteria:

- Working proof-of-concept demonstrating NGINX pipeline infrastructure and architecture (PA-OC-00)

- SSH/RDP access to NGINX targets confirmed; deployment process documented (PA-OC-01)

- SOC 2 compliance requirements documented; secrets identified with remediation approach agreed (PA-OC-01)

- Data classification report reviewed by GRC; Dynamo access governance signed off (PA-OC-01)

- Runner model, secrets approach, SOC 2 baseline, and data classification decisions resolved (PA Constraint Summary)

4.4 Workstream: Learning System (readiness only)

| # | Activity | Owner | Timing | Deliverable |
| --- | --- | --- | --- | --- |
| LS-0.1 | Confirm prerequisites: VI monitoring/data flowing; PA inventory/Git/pipeline early progress; Workstream B/C confirmation of LS dependencies | Workstream A lead | Ongoing | Written go/no-go for LS-S0 (see §3a) |
| LS-0.2 | Align LS roadmap to M7 themes (remediation, DORA, knowledge transfer, learning loop) vs PDF timing (Month 18) | Workstream A lead + sponsor | Before LS-S1 kickoff | Milestone mapping note (PDF vs lsStages dates) |

Exit Criteria:

- LS-S0 blockers explicitly documented (VI monitoring/data, PA inventory/Git progress, Workstream B/C confirmation)

- No LS-S1 platform selection until prerequisites are substantively met

- M7 outcomes (remediation, DORA, knowledge transfer, learning loop) are understood as program-level targets

- LS roadmap aligned to M7 themes vs. PDF timing (Month 18)

# 5. Phase 1: Foundation and platform rollout

Objective: Put core platforms and structure in place — work system configured, Dynatrace deployed, NGINX configs on path to version control.

5.1 Work Management

| # | Activity | Owner | Timing | Deliverable |
| --- | --- | --- | --- | --- |
| WM-1.1 | Tool selected and system configured | Dynamo + DMSi | Weeks 3–5 | WM-OC-03 |
| WM-1.2 | Existing queue disposition (360) | Dynamo + Bryan | Weeks 4–6 | WM-OC-04 |

5.2 Visibility Infrastructure & Proactive Detection

| # | Activity | Owner | Timing | Deliverable |
| --- | --- | --- | --- | --- |
| VI-1.1 | Dynatrace platform and integrations deployed | Dynamo | Weeks 3–4 | VI-OC-03 |
| VI-1.2 | Host fleet instrumented | Dynamo + Andy | Weeks 4–5 | VI-OC-04 |
| VI-1.3 | Begin parallel log migration track | Dynamo + Andy | Weeks 4–9 | VI-OC-06 progression |

5.3 Pipeline Automation

| # | Activity | Owner | Timing | Deliverable |
| --- | --- | --- | --- | --- |
| PA-1.1 | Migration path and runner infrastructure defined | Dynamo + Andy | Weeks 4–6 | PA-OC-03 |
| PA-1.2 | Configurations in version control | Dynamo + Andy | Weeks 6–10 | PA-OC-04 |

Phase 1 Exit Criteria:

- Dynatrace tenant provisioned with RBAC, ActiveGates deployed, and PagerDuty integration operational (VI-OC-03)

- OneAgent deployed on all in-scope hosts; infrastructure metrics flowing (VI-OC-04)

- All NGINX configs migrated to GitHub; no secrets in repo; CODEOWNERS and branch protection configured (PA-OC-04)

- Work management tool selected, configured to match agreed workflow states, and ready for use (WM-OC-03)

- All 559 open 360 cases reviewed, categorized, and dispositioned into curated backlog (WM-OC-04)

- Note: WM-OC-07/09 may extend past May per WM-WSB timeline constraints

# 6. Phase 2: Operational pipelines and trusted telemetry

Objective: Automated config pipeline running; drift detection live; external availability and application telemetry operational; initial WM adoption.

6.1 Pipeline Automation

| # | Activity | Owner | Timing | Deliverable |
| --- | --- | --- | --- | --- |
| PA-2.1 | Build + deploy pipelines operational | Dynamo (+ Rex deploy) | Weeks 10–13 | PA-OC-05, PA-OC-06 |
| PA-2.2 | Drift detection operational (parallel where dependencies allow) | Dynamo | Weeks 7–11 | PA-OC-07 |

6.2 Visibility Infrastructure & Proactive Detection

| # | Activity | Owner | Timing | Deliverable |
| --- | --- | --- | --- | --- |
| VI-2.1 | Infrastructure visibility validated (iterative) | Dynamo + Andy | Week 6–10 | VI-OC-05 |
| VI-2.2 | External availability monitoring | Dynamo + Andy | Weeks 5–7 | VI-OC-07 |
| VI-2.3 | Application telemetry operational | Dynamo + Brent | Weeks 7–9 | VI-OC-08 |

6.3 Work Management

| # | Activity | Owner | Timing | Deliverable |
| --- | --- | --- | --- | --- |
| WM-2.1 | Initial adoption validated | Dynamo + team | Weeks 5–9 | WM-OC-05 |
| WM-2.2 | Full category coverage and reactive visibility | Dynamo + team | Weeks 9–14 | WM-OC-06 |

Phase 2 Exit Criteria:

- Build pipeline operational: GitHub Actions workflow running, config linting/validation passing (PA-OC-05)

- Deploy pipeline operational: Ansible deployment via runner, rollback tested (PA-OC-06)

- Drift detection operational: scheduled comparison running, alerting integrated (PA-OC-07)

- Normal ranges documented for infrastructure; SLOs defined with error budget alerts configured (VI-OC-09)

- All planned work categories in the system; PagerDuty integration creating follow-up items (WM-OC-06)

- Commitment tiers in use; capacity ratio (planned vs. reactive) visible by week (WM-OC-06)

# 7. Phase 3: Validation, enforcement, and institutionalization

Objective: Prove reliability; enforce config-as-code; tune alerting; complete WM board accuracy and scorecard; close legacy monitoring where validated.

7.1 Pipeline Automation

| # | Activity | Owner | Timing | Deliverable |
| --- | --- | --- | --- | --- |
| PA-3.1 | Pipeline reliability validated (iterative — target 90%+) | Dynamo + Andy | Weeks 12–16 | PA-OC-08 |
| PA-3.2 | Config-as-code enforced | Dynamo + Andy | Weeks 16–20 | PA-OC-09 |
| PA-3.3 | Pipeline fallback (if reliability fails) | Dynamo + Andy | Triggered | PA-OC-10 |

7.2 Visibility Infrastructure & Proactive Detection

| # | Activity | Owner | Timing | Deliverable |
| --- | --- | --- | --- | --- |
| VI-3.1 | Baselines and data quality validated | Dynamo + Andy | Weeks 9–11 | VI-OC-09 |
| VI-3.2 | Alerting optimized; persona views; PagerDuty integration | Dynamo | Weeks 11–13 | VI-OC-10 |
| VI-3.3 | Proactive operations validated | Dynamo | Week 13+ | VI-OC-11 |
| VI-3.4 | Legacy systems decommissioned | Dynamo + Andy | Weeks 10–14 | VI-OC-12 |

7.3 Work Management

| # | Activity | Owner | Timing | Deliverable |
| --- | --- | --- | --- | --- |
| WM-3.1 | Board accuracy validated | Dynamo + team | Weeks 12–16 | WM-OC-07 |
| WM-3.2 | Flow metrics and scorecard operational | Dynamo + team | Weeks 10–14 | WM-OC-08 |
| WM-3.3 | Prioritization drives execution | Dynamo + leadership | Weeks 14–18 | WM-OC-09 |

Phase 3 Exit Criteria:

- Build, deploy, and drift pipelines, each achieving 90%+ success rate over a 2-week window (PA-OC-08)

- Config-as-code enforced for NGINX critical configs at 80%+ coverage; manual changes blocked or flagged (PA-OC-09)

- Synthetic + infrastructure monitoring detecting customer-visible issues within 10 minutes; MTTD sustained at target (VI-OC-11)

- Legacy systems (Elastic, CheckMK) decommissioned or decommission recommendation presented (VI-OC-12)

- Board freshness sustained at 90%+ for 3 consecutive weeks; no competing shadow tracking systems (WM-OC-07)

- Team pulls work from the system; priority changes reflected in execution; stakeholders check status via the board (WM-OC-09)

- Note: WM-OC-09 may extend into June per WM-WSB timeline constraints

# 8. Phase 4: Replication and advanced capabilities (conditional)

Objective: Extend proven patterns and mature advanced VI/LS capabilities only when triggers are met.

| # | Activity | Owner | Deliverable |
| --- | --- | --- | --- |
| PA-4.1 | Pipeline pattern replication (non-NGINX config types) | Leadership decision + Dynamo | PA-OC-11 |
| VI-4.1 | Predictive operations / advanced capabilities | Dynamo | VI-OC-14 |
| VI-4.2 | A2W monitoring readiness | Trigger: A2W date | VI-OC-13 |
| LS-4.1 | LS-S1 through LS-S6 (platform plan → observability → patterns → playbooks → error budgets → continuous improvement) | After LS-S0 | Per §3a and lsStages in capability map; M7 outcomes from Phase 2 PDF as program north star |

# 9. Cross-Workstream dependencies (Workstream A ↔ others)

Consolidated from PA-WBS §8, VI-WSB §8, and WM-WSB §8. Full tables and coordination notes remain in those documents.

| ID | From / To | Summary |
| --- | --- | --- |
| PA-CW-01 … PA-CW-05 | PA ↔ VI, WM, LS, IRP | Security baseline shared with VI; WM tracks pipeline work; SDLC events to Dynatrace; IRP update before PA-OC-09 |
| VI CW-01 … CW-07 | VI ↔ WM, WSD, WSB, WSC, PA | Scorecard timing; synthetic monitoring vs tiered service; PagerDuty platform-agnostic; SDLC events from PA; executive dashboard data; pod-based routing; status page templates |
| WM-CW-01 … WM-CW-04 | WM ↔ WSD, WSB, WSC, VI | Scorecard metric alignment; escalation categories; contingent tool overlap; dashboards reference WM data |

# 10. Risk register (high-level)

Outstanding Type 1 (one-way door) decisions consolidated from PA-WBS, VI-WBS, and WM-WBS.

Type 1: Decisions are irreversible and require deliberate process and explicit sign-off. Full risk registers remain in the individual WBS/WSB documents.

Type 2: Decisions can be found in the Confluence project plan

| ID | Stream | Decision | Owner | Required By | Status |
| --- | --- | --- | --- | --- | --- |
| PA-D-02 | PA | Secret management approach (GitHub Secrets, Vault, AWS Secrets Manager) | Dynamo + Andy | PA-OC-01 exit | OPEN |
| PA-D-03 | PA | SOC 2 compliance standard for pipeline artifacts | Andy + Ryan | PA-OC-01 exit | OPEN |
| PA-D-07 | PA | GitHub runner deployment model (AWS account, VPC) | Andy + Dynamo | PA-OC-03 exit | OPEN |
| PA-D-08 | PA | Ansible automation feasibility (can it run without human interaction?) | Dynamo + Rex | PA-OC-03 exit | OPEN |
| PA-D-10 | PA | Config-as-code enforcement policy (what happens when pipeline is the only path?) | Andy + leadership | PA-OC-08 exit | OPEN |
| PA-D-13 | PA | CAB change request process for pipeline deployments | Andy + Ryan | PA-OC-04 entry | OPEN |
| VI-D-01 | VI | Dynatrace SaaS vs. Managed deployment | Andy Meyers | VI-OC-01 exit | OPEN |
| VI-D-02 | VI | Licensing model (DPS vs. Classic) -- multi-year contract commitment | DMSi Procurement + Dynamo | VI-OC-02.4 | OPEN |
| VI-D-16 | VI | Elastic decommission -- data archival before shutdown (irreversible) | Andy + Leanne (GRC) | VI-OC-12.1 | OPEN |
| VI-D-17 | VI | Log retention period (35/90/custom days) | Andy + Leanne (GRC) | VI-OC-02.3 | OPEN |
| WM-D-04 | WM | Relationship between work management system and 360 (replace vs. promote) | Bryan + Andy + Brent | WM-OC-03.1 | OPEN |